Eco-Schools Action Plan	SCHOOL NAMEL: St Francis Xavier’s Primary School

Eco-Schools Topic 1:	Litter and Waste
Date Range of this Plan: 2021 to 2022

Your school’s Sustainable Development Goal: Goal 15- Life on Land

How will our actions contribute towards our chosen SDG? Goal 15- Life on land- Our Actions will contribute towards our SDG by reducing the amount of litter in our school and community and recycling more litter instead of it going to landfill.
Aim(s) / What do we aim to achieve? Why? / You can have the same aim for all actions, or different aims for different actions.	Actions / How are we going to achieve our aims? What actions will we do? / Minimum 3 actions per topic.	Who? / When? / Who is responsible for the action? Who else will help?/ When will it happen?	Measuring: / What, how and when will we measure to monitor any changes?	Evaluation/Development: / What did we learn from our monitoring? / How far did our actions go towards achieving our aims? / Could we have done anything differently?
Reduce the amount of litter in our playground. To work towards achieving SDG 15. / Better understand the litter situation in the school.	Evaluate current litter issue. Carry out a litter audit of the playground.	Eco group, Janitor. Oct 2021	Carry out a litter survey within the school grounds to find out what type of litter is being dropped, what the worst spots are, and if it is coming from outside the school. / We plan to carry out this survey each year to re assess the situation.	The main litter found was crisp and sweet packets. The main area of the playground where litter was found with the tree/den area.
Reduce the amount of litter in our playground. To work towards achieving SDG 15. / Better understand the litter situation in the school.	Evaluate success of the previous litter rota / competition and decide on new litter strategy/ action plan.	Eco group, Janitor. / Oct 2021	Litter pickers and janitor to monitor the litter situation. / Re evaluate each term.	Current litter strategy is working well and children like being able to volunteer to litter pick when they like and enjoy the rewards form the janitor.
Reduce the amount of litter in our playground. To work towards achieving SDG 15.	Write to the council to ask for more bins	Eco Group with help from Mrs McQuade. Oct 2021	Litter pickers to monitor litter levels.	The council replied to say that they can only issue bins for local areas and not the school. We evaluated the need for additional bins in the local area and decided that there was enough. We have decide just to reposition our current bins to tackle the litter problem in the wood area.
Reduce the amount of litter in our playground. To work towards achieving SDG 15.	Janitor to continue to organise litter pickers	Eco group and Janitor. / Oct 2021- ongoing	Litter pickers and janitor to monitor the litter situation.	Litter situation is improving and this system is working well.
Reduce the amount of litter in our playground. To work towards achieving SDG 15.	Reposition bins to the den area	Eco group and Janitor. / Oct 2021- ongoing	Litter pickers and janitor to monitor the litter situation.	This has greatly reduced the amount of litter in our playground.
Reduce the amount of litter in our playground. To work towards achieving SDG 15.	Include littering in the playground reflection sheet to deter littering.	SMT / Nov 2021- ongoing	Litter pickers and janitor to monitor the litter situation.	This has helped to reduce the amount of litter in our playground.
Reduce the amount of litter in our playground. To work towards achieving SDG 15. / Raise awareness and ownership of this Eco topic and SDG.	Create a school litter policy, submit to Falkirk council	Eco group, Ella Gorman waste services. / Nov 2021- ongoing	Litter pickers and janitor to monitor the litter situation.	We have updated the previous litter strategy to reflect our proactive approach to littering. / We feel this would be better with input from the whole school so as soon as we are able, we plan to hold a whole school litter assembly to share our litter strategy and ask for feedback/ input from the rest of the school.
Celebrate our cluster schools Eco achievements, share good practice across the authority, pledge to continue Eco schools and Laudato Si agenda. Discuss local Eco related issues with councillors.	Organise COP26 cluster school event. Discuss school litter problems with local councillors.	Faith in Action group. / Nov 2021- annual		We were able to discuss the wider issue of litter in our community oat the conference and following this have plans to work more closely with Falkirk Council litter enforcement officers to help tackle this issue in our community.
Reduce the amount of litter in our playground and local area. To work towards achieving SDG 15.	School and community litter pick	Eco group, teachers, parents and grandparents. / Nov 2021-ongoing	We measured the amount of litter collected from our school and community litter pick and compared it to the previous amount collected in 2019.	In all areas, the school and local community, there was less litter to be collected than in previous years. This is an encouraging sign that the litter situation in our area is improving. We plan to hold another community litter event in term 4.
Reduce the amount of litter in our local area. To work towards achieving SDG 15.	Adopting an area, Sunnyside, to have a class a month to do a litter pick for.	Eco group, Ella Gorman, class teachers, whole school, parent volunteers. / Nov 2021- ongoing	Every month when we carry out a litter pick of the area, we will record how many bags of litter we have collected and chart the increase/decline month on month. We will also carry out litter surveys to identify the main types of litter and try to introduce measures to stop the littering.	We are working with Ella Gorman from waste services on this project. The adoption of the area for litter picking and monitoring has been approved by the council and the monthly clean ups will start in March 2022.
Reduce the amount of waste produced by our school. To work towards achieving SDG 15.	Recycle whiteboard pens	Whole school, Mrs McQuade- link up with Maddison Primary School / Nov 2021- ongoing	Every term the number of whiteboard pens collected are recorded and then delivered to Maddison Primary School	Month on month the usage is similar and significant so this action will continue.
Raise awareness of Eco issues across the school in line with COP 26. Including littering and pollution on land and under the Sea.	Every class to focus on an Eco themed class topic in term 2.	SMT, class teachers, pupils. / Nov 2021- ongoing.	Pupil voice in deciding the area of sustainability to focus on and involvement in the planning of the topics. Evaluation at the end of the topic to evaluate impact and learning.	Pupils were very engaged in this learning. Sustainability topics will now be covered across the school every year.
To raise awareness and the profile of the Litter agenda. To help us better understand the problem associated with litter.	Plan school assembly to explain / raise awareness of litter competition.	Eco group / Dec 2021- ongoing	Raised awareness of litter and all Eco topics	We have still been unable to start our monthly Eco assemblies due to covid restrictions but plan to do so as soon as we can.
To raise awareness and the profile of the Litter agenda. To help us better understand the problem associated with litter.	Enter Falkirk Council Waste services competition to design a logo for bin lorries.	Whole school / Dec 2021	Uptake of the competition across the school.	Whole school participation in the competition.
Eco litter code to be designed by pupils. Short snappy code that everyone can remember.	Competition for new Eco litter code.	Eco group, whole school. / Jan 2022- ongoing	Pupil involvement
To raise awareness and the profile of the Litter agenda. To help us better understand the problem associated with litter.	Litter workshop to be help with Eco group.	Ella Gorman- Falkirk council waste services. / Jan 2022	Feedback from teachers and classes	Feedback form both teachers and pupils was very positive. They described the workshops as interactive, informative and fun.
To raise awareness and the profile of the Litter agenda. To help us better understand the problem associated with litter.	Litter workshop to be held with all year groups	Falkirk Council Waste Services / Primary 5-7 pupils / Jan 2022		Ella has now help litter workshops for Primary 5,6 and 7 classes. We now intend for these classes to share the learning with children in primary 1-4 by delivering litter workshops for these classes.
To raise awareness and the profile of the Litter agenda.	Litter competition to ‘design a bin’	Eco group, whole school. / Jan 2022
To raise awareness and the profile of the Litter agenda.	Monthly Eco assemblies to keep pupils and staff updated with litter action plan	Eco group / Ongoing from Feb 2022
Reduce the amount of litter in our playground. To work towards achieving SDG 15.	Garden group to help with litter picking.	Garden Group / Ongoing
To raise awareness and the profile of the Litter agenda.	Make a display on the notice board about the harmful effects of litter	Eco group / Jan 2022
To raise awareness and the profile of the Litter agenda.	Work with Falkirk Council Waste Services on fly tipping within our community campaign. Make posters for school and local community to highlight the issues with littering and specifically fly tipping	Eco group, whole school / Feb/March 2022
To help us better understand the problem associated with litter.	Organise a visit to local recycling plant.	Ella Gorman / TBC
Reduce the amount of litter in our local area. To work towards achieving SDG 15.	Litter picking with local care home residents to tidy up their outside area.	Blether Buddies, NewCarron Care home / March 2022- ongoing	Measure the amount of litter collected each time and monitor.
Reduce the amount of litter in our school. To work towards achieving SDG 15.	Tidy up our corridor campaign	Eco group, whole school / Feb/March 2022		Not outside much this month due to rain. Decided to start an inside litter campaign to clean our corridors. / Children eating snacks in class and in corridors at break times. After campaign litter in corridor reduced to almost none.
Reduce the amount dog fouling in our school and local area. To work towards achieving SDG 15.	Dog fouling campaign	Eco group, Falkirk Council Waste services / March 2022